## Sheet1
S No | Phase | Feature | Scenario | testcase | testcase intent | testcase detailed flow | test status | Debug status | Exp. Closure date
1 | P1 | Register
| P1 |  | register reset | test_reg_reset | Check the reset values of all the registers against the specification values. | 1. Apply and release reset -> Registers taking reset values. 2. Read all registers 3. Check the read value with the spec. value. | PASSED
| P1 |  | register write read | test_reg_wr_rd | Check if the register writes and reads are happening properly. | 1. Write all the registers in random order 2. Read all the registers in random order 3. Compare write data with read data. | FAILED | 1. W1C type of field causing mismatch.
2 | P1 | Full duplex MAC transmit and receive
| P1 |  | 10 Mbps | test_mac_10mbps | Check MAC transmit and receive at 10Mbps | 1. Configure MAC for 10Mbps mode 2. Transmit and receive frames at 10Mbps
| P1 |  | 100 Mbps | test_mac_100mbps | Check MAC transmit and receive at 100Mbps | 1. Configure MAC for 100Mbps mode 2. Transmit and receive frames at 100Mbps
| P1 |  | 100 Mbps | test_mac_tx_rx_100mbps | Check MAC transmit and receive at 100Mbps | 1. Configure MAC for 100Mbps mode 2. Transmit and receive frames at 100Mbps
3 | P2 | Full duplex mode
|  |  | Tx Flow control | test_fd_tx_flow_control | Check transmit flow control in Full duplex mode. | 1. Configure MAC for transmit in Full duplex mode. 2. Implement PHY BFM to generate Pause frame randomly with a random Pause time value. 3. Check if Tx MAC is implementing the required Pause time.
|  |  | Rx Flow control | test_fd_rx_flow_control | Check receive flow control in Full duplex mode. | 1. Configure MAC for receive mode. 2. Configure the design to generate Pause frame with random Pause time value. 3. Check if design is generating the Pause frames as per the configuration 4. PHY BFM should implement the required Pause time based on the time when incoming frames are received.
|  |  | Tx-Rx Flow control | test_fd_tx_rx_flow_control | Check transmit and receive flow control in Full duplex mode. | 1. Configure MAC for both transmit and receive modes. 2. Generate Pause frame with random Pause time value. 3. Implement PHY BFM to generate pause frames 4. PHY BFM should implement the required Pause time based on the time when incoming frames are received.
|  |  | Pass all | test_fd_passall | Check if passall configuration is storing all the frames including Pause frames to the buffer. | 1. Configure MAC with passall feature enabled 2. Check if incoming Pause frames are stored in to the buffer memory. 3. Disable passall feature, check if Pause frame are discarded after processing for flow control.
4 | P2 | Half duplex mode
|  |  | Collision detection and retransmission | test_hd_collision_det_retransmission | Check if MAC is able to implement CSMA/CD protocol. | 1. Configure MAC for transmit mode 2. Implement PHY BFM to generate collisiondet signal as '1' at random intervals 3. Transmit ethernet frame with random delays 4. Check if CSMA/CD protocol works, check if frame are getting retransmitted on collision detection.
|  |  | Back off algorithm | test_hd_backoff_algorithm | Check if MAC is implementing the backoff algorithm | 1. Configure MAC for transmit mode 2. Implemente PHY BFM to generate collisiondet signal as '1' at random intervals more frequently so that lot of collisions happen, so that lot of back offs should happen. 3. Transmit ethernet frame with random delays 4. Check if backoff algorithm is working fine.
5 | P2 | Inter packet gap
|  |  | Interpacket gap | test_interpacket_gap | Check IPGT, IPGR1, IPGR2 register behavior. | 1. Configure IPGT, IPGR1, IPGR2 register for different possible values 2. Generate frames with random inter packet gap and check if they are collected properly.
6 | P2 | Different transmission
|  |  | unicast | test_mode_unicast | Check unicast mode of MAC | 1. Configure MAC for unicast mode(register programming and MAC DA value). 2. Transmit the frames
|  |  | Multi cast | test_mode_multicast | Check the multicase mode of MAC | 1. Configure MAC for multicast mode(register programming and MAC DA value). 2. Transmit the frames 3. Check whether multi cast is working 4. Implement PHY BFM also generate frames in multi cast mode.
|  |  | Broadcast | test_mode_broadcast | Check the broadcast mode of MAC | 1. Configure MAC for broadcast mode(register programming and MAC DA value). 2. Transmit the frames 3. Check whether broad cast is working 4. Implement PHY BFM also generate frames in broad cast mode.
7 | P2 | Interrupt
|  |  | Receive control frame | test_fd_tx_flow_control | Check interrupt generation on transmit flow control in Full duplex mode. | 1. Configure MAC for transmit mode 2. Implement PHY BFM to generate Pause frame randomly with random Pause time value. 3. Check if Tx MAC is implementing the required Pause time. 4. Check if interrupt is generated to the RISC.
|  |  | Transmit control frame | test_fd_rx_flow_control | Check interrupt generation on receive flow control in Full duplex mode. | 1. Configure MAC for receive mode. 2. Generate Pause frame with random Pause time value. 3. Check if the PHY BFM is implementing the required Pause time based on the time when incoming frames are received. 4. Check if interrupt is generated to the RISC.
|  |  | BUSY | test _interrupt_busy | Check if Busy interrupt is generated when buffer is full and frame is received. | 1. Keep the buffer full. 2. Implement PHY BFM to generate frames 3. Check if Busy interrupt is generated.
|  |  | Receive error | test_interrupt_receive_error | Check if receive error interrupt is getting generated | 1. Implement PHY BFM to drive MRxErr=1 at random intervals. 2. Check if interrupt is getting generated
|  |  | Receive frame | test_interrupt_receive_frame | Check if receive frame interrupt is generated | 1. Configure MAC for receive mode 2. Implement PHY BFM to generate frames 3. Check if interrupt is generated (INT MASK is enabled)
|  |  | Transmit error | test_interrupt_transmit_error | Check if transmit error interrupt is getting generated | 1. Configure MAC to drive MTxErr=1 at random intervals. 2. Check if interrupt is getting generated
|  |  | Transmit frame | test_interrupt_transmit_frame | Check if transmit frame interrupt is generated | 1. Configure MAC for transmit mode 2. Transmit teh frames 3. Check if interrupt is generated (INT MASK is enabled)
8 | P3 | Various types of packets
|  |  | Small packet | test_packet_len_small
|  |  | Normal packet | test_packet_len_normal
|  |  | large packets | test_packet_len_large
|  |  | CRC enabled | test_crc_enabled
9 | P3 | packet length
46 to 1500, 8870, smaller packets
10 | P3 | Loopback
|  |  | packet loopback | test_mac_loopback | Configure MAC in loopback mode. Check if transmitted packed is received. | 1. MODER.LOOPBK=1 2. Generate Frame with Length=100 bytes
11 | P3 | Promiscuous mode
|  |  | Promiscuous mode | test_promiscuous | Configure MAC in Promiscuous mode and check if accepts all the packets. | 1. MODER.promiscuous = 1 2. PHY BFM generates all types of packets(Unicast, multi cast, and broadcast mode) 3. Check if MAC RX block is accepting all these packets.
12 | P3 | MII Management module
|  |  | Clock division | test_mii_clock_division
|  |  | MIIONPRE | test_mii_miionpre
|  |  | Write command | test_mii_write_command
|  |  | Read command | test_mii_read_command
|  |  | Scan status | test_mii_scan_status
13 | P3 | Error scenarios
|  |  | Dribble nibble | test_error_dribble_nibble
|  |  | Invalid symbol | test_rxbd_invalid_symbol
|  |  | Overrun | test_rxbd_overrun
|  |  | Underrun | test_txbd_underrun
|  |  | Too Long | test_rxbd_too_long
|  |  | Short | test_rxbd_short
14 | P3 | TxBuffer descriptors
|  |  | Tx BD Ready | test_txbd_tx_bd_ready
|  |  | IRQ | test_txbd_irq
|  |  | Wrap | test_txbd_wrap
|  |  | Underrun | test_txbd_underrun
|  |  | RTRY | test_txbd_rtry
|  |  | Retrasmission Limit | test_txbd_transmission_limit
|  |  | Late collision | test_txbd_late_collision
|  |  | Defer indication | test_txbd_defer_indication
|  |  | CS lost | test_txbd_cs_lost
15 | P3 | RxBuffer descriptors
|  |  | Empty | test_rxbd_empty
|  |  | IRQ | test_rxbd_irq
|  |  | Wrap | test_rxbd_wrap
|  |  | Control frame | test_rxbd_control
|  |  | Miss | test_rxbd_miss
|  |  | Overrun | test_rxbd_overrun
|  |  | Invalid Symbol | test_rxbd_invalid_symbol
|  |  | Tool long | test_rxbd_too_long
|  |  | Short frame | test_rxbd_short
|  |  | Rx CRC error | test_rxbd_rx_crc_error
|  |  | Late collision | test_rxbd_late_collision
16 | P3 | Deferral
deferral with transmission failure
deferral with transmission success